## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | Intern Analysis
PROJECT ID
PROJECT MANAGER | Jayanth GS
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2020-07-10 | Visualizations were not being displayed values due to NaN values | Technical | NA | Check for NaN values during data pre-processing | Clean data before applying visualizations | Project Lead | Closed
2 | 2020-07-20 | Labels were not visible | Technical | Large size of labels | Reduce size of labels or rotate values | Rotated label to make it visible | Project Lead | Closed
3 | 2020-07-23 | classification model selection | Technical | NA | Try different models before selecting best | Applied 4 different models | Project Lead | Closed
4 | 2020-07-28 | Preparing a classification report | Technical | What parameters do you compare models on? | Learnt how to generate classification report | Applied classification reports to all models to compare | Project Lead | Closed
5 | 2020-07-30 | Converting ipynb to py file and modifying code for i/p and o/p | Technical | NA | Modify code on python shell | The code has been altered to fit the necessary i/p and o/p standards | Project Lead | Closed
6 | 2020-07-30 | Generating PDF file | Technical | NA | Outputs are not properly visible, check documentation for savefig | bbox=tight has been added to the code | Project Lead | Closed