## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Intern Analysis
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-07-06
PROJECT DELIVERABLE | Eligibility of Interns |  | EXECUTION PHASE END DATE: |  | 2020-07-31
PROJECT SCOPE | Cloud Counselage Pvt. Ltd. Interns
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | Completed
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Project Initiation
| 1.1 Understand the Software Development Life cycle | 2 | 2020-06-15 | 2020-06-21 | 7 | COMPLETED
| 1.2 Understand the Problem statement, i.e. Intern Eligibility | 4 | 2020-06-15 | 2020-06-21 | 7 | COMPLETED
| 1.3 Understand AGILE project management system | 4 | 2020-06-15 | 2020-06-21 | 7 | COMPLETED
| 1.4 Create a Project Charter | 5 | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
| 1.5 Requirement Gathering | 5 | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
2. Project Planning
| 2.1 Design a Project Model | 12 | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
| 2.2 Complete the SRS Document | 12 | 2020-06-22 | 2020-06-28 | 7 | COMPLETED
| 2.3 Create a Project Plan | 48 | 2020-06-29 | 2020-07-05 | 7 | COMPLETED
3. Project Execution
| 3.1 Finalize Project Design and Plan | 2 | 2020-06-29 | 2020-07-05 | 7 | COMPLETED
| 3.2 Collect relevant dataset | 12 | 2020-06-29 | 2020-07-05 | 7 | COMPLETED
| 3.3 Clean and pre-process dataset | 24 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
| 3.4. Create Development Log | 3 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
| 3.5 Creating RAID log | 12 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
| 3.6 Divide dataset into testing and training data | 24 | 2020-07-06 | 2020-07-12 | 7 | COMPLETED
| 3.7 Create data visualization models to build graphs | 48 | 2020-07-13 | 2020-07-19 | 7 | COMPLETED
| 3.8 Answer required questions using the models | 48 | 2020-07-13 | 2020-07-19 | 7 | COMPLETED
| 3.9 Plot the required relationships between the data | 4 | 2020-07-13 | 2020-07-19 | 7 | COMPLETED
| 3.10 Update RAID Log | 2 | 2020-07-13 | 2020-07-19 | 7 | COMPLETED
| 3.11 Update Development Log | 1 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
| 3.12 Identify the best binary classifier | 24 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
| 3.13 Classify data into eligible/non-eligible | 24 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
| 3.14 Update RAID log | 2 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
| 3.15 Update Development Log | 2 | 2020-07-20 | 2020-07-26 | 7 | COMPLETED
4. Project Testing | [5 empty] | COMPLETED
| 4.1 Compare training and test data | 12 | 2020-07-27 | 2020-07-31 | 7 | COMPLETED
| 4.2 Verify all models and visualizations | 12 | 2020-07-27 | 2020-07-31 | 7 | COMPLETED
| 4.3 Finalize all documentation | 12 | 2020-07-27 | 2020-07-31 |  | COMPLETED
5. Project Closure |  |  | 2020-07-27 | 2020-07-31 |  | COMPLETED