## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0
| Project title: | Intern Analysis |  | Project Id: |  | Project Manager: | Jayanth GS |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-30 | Project Team Lead: | Sakshi Chahande |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 5 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Inability to complete project on time | Delivery of project will be delayed | Project Plan has been created to finish development on time | Project Manager | High | 2 | Closed | Risk
2 | [8 empty] | Assumption
3 | Issue | System does not have the required software, i.e. Jupyter Notebook | Project will not be developed | Add Jupyter Notebook to prerequisite for development of project. Download Jupyter notebook. | Project Team Lead | Critical | 1 | Closed | Issue
4 | [8 empty] | Dependency
5 | Dependency | Cloud Counselage Pvt. Ltd. Must give permission to access data | Project data will be insufficient/not appropriate | Data has been supplied by Manager | Project Manager | High | 4 | Closed
6 | [8 empty] | Open
7 | Assumption | Data given to us is verified by manager | Data inaccuracy | Verify information with manager | Project Manager | Negligible | 5 | Closed | Closed
8
9 | Risk | Classification model selected is not appropriate | The F1 score will be less.and the model will not be as accurate | Have compared multiple classification models to select the best one | Project Team Lead | Critical | 3 | Closed | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24